# Project Proposal

Prepared for Northwind Coffee Roasters

Photography · Brand Design · Motion   ·   2026

Prepared by Mara Lindqvist, Creative Director

# 1. Overview

Aurora Visuals is a full-service creative studio specialising in photography, brand design, and motion. This proposal outlines the scope, schedule, and investment for a refreshed visual identity and launch campaign for Northwind Coffee Roasters.

- Full-service studio: photography, brand identity, and motion under one roof.

- Senior creative leads on every engagement — no hand-offs to juniors.

- Licensed, watermark-protected delivery so client assets stay controlled.

- Average 12-day turnaround from brief to final delivery.

# 2. Services

- The engagement draws on the following studio services. Rates are fixed for the duration of the project.

| - SKU | - Service | - Category | - Rate |
| --- | --- | --- | --- |
| - AV-PH-01 | - Studio photography (half day) | - Photography | - $1,200 |
| - AV-PH-02 | - On-location photography (full day) | - Photography | - $2,600 |
| - AV-BR-01 | - Brand identity system | - Brand Design | - $8,500 |
| - AV-BR-02 | - Pitch & sales deck design | - Brand Design | - $3,400 |
| - AV-MO-01 | - Social motion pack (10 clips) | - Motion | - $4,200 |
| - AV-MO-02 | - Brand film (60s) | - Motion | - $9,800 |

# 3. Timeline

- Week 1 — Discovery workshop and creative brief.

- Week 2 — Studio and on-location photography.

- Week 3 — Brand system and pitch-deck design.

- Week 4 — Motion pack production.

- Week 5 — Review, revisions, and watermark-protected delivery.

# 4. Investment

- A summary of the fixed-fee investment by phase:

| - Phase | - Deliverable | - Fee |
| --- | --- | --- |
| - Photography | - Studio + on-location shoot | - $3,800 |
| - Brand design | - Identity system + pitch deck | - $11,900 |
| - Motion | - Social pack + brand film | - $14,000 |
| - Total | - Fixed project fee | - $29,700 |

# 5. Terms & Resources

- Full terms, licensing, and the studio portfolio are available online:

- · Master services agreement

- · Asset licensing & watermark policy

- · Studio portfolio

- · Review and approve this proposal online

# 6. Acceptance

- To proceed, sign below or approve the proposal online. Work starts within two weeks of sign-off.

- For Northwind Coffee Roasters: ____________________________   Date: ____________

- For Aurora Visuals: Mara Lindqvist, Creative Director